## Instructions
RISK MANAGEMENT LOG
Column | Instructions For Completing This Document
Complete the Project Name, NC, Project Manager Name, and Project Description fields
For each risk identified, complete the following:
A | ID: A unique ID number used to identify the risk in the risk tracking log.
B | Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
C | Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
D | Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue.
E | Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
F | Risk Description: This column should be populated with a description of the risk.
G | Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
H | Risk Area: This column should be populated with the appropriate risk area.
I | Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
J | Trigger: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
K | Risk Response Strategy: This column should be populated with the preferred risk response strategy.
L | Response Strategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
M | Contingency Plan: This column should be populated with a description of the risk contingency plan.
Column | Instructions For Changing the Contents of Drop-Down Menus
C, D, H | Highlight the cell of which you wish to change the content of the drop down menu. From the file menu click "Data" -> "Validation" and change the content of the source field
Column | Instructions For Filtering Data
Any | Highlight the header of the cell you wish to filter data on From the file menu click "Date" -> "Filter" ->"Auto Filter" Then select your filter criteria from the drop down menu that appears on your header cell

## Risk_Tracking_Log
RISK MANAGEMENT LOG | [7 empty] | RISK MANAGEMENT LOG
Project Name: |  |  | Pharmacy Error Tracker |  |  |  |  | Project Name: | Pharmacy Error Tracker
National Center: |  |  | CSU |  |  |  |  | National Center: | CSU
Project Manager Name: |  |  | James Tulip |  |  |  |  | Project Manager Name: | James Tulip
Project Description: |  |  | Creation of a single page mobile web application |  |  |  |  | Project Description: | Creation of a single page mobile web application
ID | Current Status | Risk Impact | Probability of Occurrence | Risk Map | Risk Description | Project Impact | Risk Area | Symptoms | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan
| Open | High | Low | Yellow | EXAMPLE: Current project skill set may not be adequate to complete all project work. The current development team has been working in a Windows 2k environment, and the current requirements are for a LINUX environment. The project schedule would require 1500 development hours of a skilled LINUX operator, and approximately 1900 to 2200 if we retrain our current resources. | EXAMPLE: If required skills are not identified or obtained, project schedule may slip and possibly restrict the accomplishment of project goals. | Project Resources Budget Schedule | EXAMPLE: Schedule approaches the required start date with no identification of required skill sets. | EXAMPLE: Four weeks prior to scheduled start date if no resource is identified with required skill set implement contingency plan. | Mitigation | EXAMPLE: Find internal resource that meets required skill set or train existing resources on LINUX. | EXAMPLE: Find resource that meets required skill set through external hiring sources.
| Open | Medium | Medium | Yellow
| Open | Low | Low | Green
1 | Open | High | Low | Yellow | Skills set of team members may not be adequate to complete project. All team members will need to learn how to use new software (Vue.js). Other software, such as Visual Studio Code and MySQL will be required to be learned or revised by some of the team members. | Skills will need to be obtained by all team members to ensure the goals of the project are accomplished | Schedule | Inability of the team to create required Technical Competency Demonstrator (TCD) by due Assessment date | Commencement on required coding for TCD has not commenced prior to 6 April | Mitigation | Team members to familiarise themselves with software | Team members to help each other with any issues identified. Also, share various tips and documentation found on using software, including YouTube clips and short courses.
2 | Open | High | Medium | Red | Team members not being able to test developments on local machine | Changes to application made by individual members will need to be pushed to remote server for testing. | Schedule Reliability of System | Overall application development becomes buggy and unreliable due to untested code being implemented | Currently team members do not have local testing environments | Mitigation | Guide to be created during Elaboration Iteration 1 to provide details on implementation of local testing environment | Team meeting where individual members are provided step-by-step instruction during meeting to implement local environment.
3 | Open | Medium | Medium | Yellow | Applications Metabase and vue.js do not meet project needs | New applications will need to be sourced | Schedule Technology Reliability of systems | Unable to execute required functions, such as visualisations | Difficulty in integrating software into project | Mitigation | Team members report issues immediately the arise | When indication start to appear that software is not compatible or doesn't work as desired, investigation starts urgently for new software to take its place
4 | Open | High | Medium | Red | Ability of customised changes to error entry form to flow through to database automatically | A main feature of the application will not be delivered | Feasibility Overall project failure | Unable to have the MySQL database automatically update to reflect changes made to the error entry form | Inability to solve issue | Contingency | Team members report issues immediately the arise | May need to remove flexibility from application.
5 | Open | Medium | Low | Green | Use cases are scheduled to be completed in an unrealistic time frame | Project milestones may not be achieved, pushing overall schedule back | Project Management Overall project failure | Team members struggling to complete required tasks by se dates | Team meetings and chat indicating tasks are running behind schedule | Mitigation | Review scheduling if required | When indication start to appear that tasks are not being completed due to workload being too heavy, the project schedule is to be reassessed to ensure project success
6 | Open | Medium | Low | Green | Team members not committing changes to version control regularly | Tasks reliant on other tasks may not be completed on time. Loss of data. | Schedule Data/Information Overall project failure | Infrequent use of version control | Lack of regular commits by one or more team members | Mitigation | Team members actively commit changes to documents/code to their branch and have changes reviewed by team for regular merging of branches. | If team member is not committing changes on a regular basis, other team members are to remind member to do so.
7 | Open | High | Low | Yellow | Loss of data due to system failure | Data loss would require project to commence from point where data/code is still available. May require the project to start from scratch meaning project will not be delivered - project failure | Data/Information Technology Reliability of systems Overall project failure | Infrequent use of version control, unreliable hardware/software being used | Team member/s are not documents/code to Bitbucket via continual, regular commits. Team member reports issues with their computer. | Contingency | Team members actively commit changes to documents/code to their branch and have changes reviewed by team for regular merging of branches. Team members to maintain their computer in good working order. | Unforeseen system failure will not be a huge issue as long as team members continually commit their documents/code. If team member is not committing changes on a regular basis, other team members are to remind member to do so.
8 | Open | High | Low | Yellow | Loss of knowledge should a team member leave the project | The knowledge lost can delay the area of the project development that the knowledge pertains to. Possibly restrict project goals achievements | Schedule Data/Information Project Resources | A team member is talking about leaving the project. A team member has received two strikes | A team member announces they are leaving the project. A team member receives three strikes | Avoidance | Sharing of knowledge gained on completing tasks with other team members. Ensure reporting of task status is open and honest | Ensure knowledge is being shared continually throughout the project. Help support team members struggling to meet required expectations, without completing their workload for them.
Note on A6: • ID: A unique ID number used to identify the risk in the risk management log.
Note on B6: • Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
Note on C6: • Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
Note on D6: • Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue. o High: Greater than 70% probability of occurrence. o Medium: Between 30% and 70% probability of occurrence. o Low: Below 30% probability of occurrence.
Note on E6: • Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
Note on F6: • Risk Description: This column should be populated with a description of the risk.
Note on G6: • Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
Note on H6: • Risk Area: This column should be populated with the appropriate risk area.
Note on I6: • Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
Note on J6: • Triggers: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
Note on K6: Risk Response Strategy: This column should be populated with the preferred risk response strategy.
Note on L6: • ResponseStrategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
Note on M6: • Contingency Plan: This column should be populated with a description of the risk contingency plan.

## DropDown_Elements (hidden)
Risk Area
Schedule
Initial Costs
Life-cycle Costs
Technical Obsolescence
Feasibility
Reliability of Systems
Dependencies/Interoperability
Surety Considerations
Future Procurements
Project Management
Overall Project Failure
Organizational/Change Management
Business
Data/Information
Technology
Strategic
Security
Privacy
Project Resources