## Sheet1
Backend Server Work
Task | Approximate Time (In hours) | Notes
Create AWS Account | 1 | Had to create the AWS account in order for the team to be able to use a cloud hosted server, this took some time as we tried Azure, Cloud Nine, and Heroku as other options first before settling on AWS. | Total Time Spent
Create AWS Red Hat Enterprise Linux (RHEL) Server | 0.25 | Initially Created a RHEL server due to the increased security available on this type of linux server, however, we ran into issues setting the server up and getting Iptables to create the correct outgoing routes | 36
Create AWS Security Group | 0.25 | Creating security groups for different access levels to the server
Create AWS Routing Rules | 0.25 | Creating routing rules for the different web applications to be able to receive and send information to and from the server.
Create AWS Ubuntu Server | 0.25 | Created an Ubuntu Server due to the issues experienced with the RHEL server that was mentioned earlier
Initial RHEL Server Setup (GIT, SSH Keys, IPTables, etc.) | 3 | There was a number of issues getting the server setup on RHEL with the Nodejs installation, we could not get the outgoing routes to work with IPTables. As a result I terminated this server
Initial Ubuntu Server Setup (GIT, SSH Keys, IPTables, etc.) | 2 | This setup worked much more easily and was abble to get the outgoing routes to work with much less difficulty.
Node Installation and Configuration | 1 | Installation of node and update of required configs to get it running, I also created a basic app.js file to ensure that the server was running and could be connected to
MySQL Installation and Configuration | 1.5 | Installation of mySQL and update of required configs and user account to get it running, there was also quite a large amount of time spent fixing remote connections to the database so that everyone could connect to the server remotely for both their applications and their versions of MySQL workbench
Metabase Installation and Configuration | 0.5 | Installation of Metabase and update of required configs and user accounts to get it running
Creation of Scripts to automate Node and Metabase startup | 3 | Created bash scripts and alias on the server so that other users could start the required applications from a single command (start-server), this then had to be amended so that we could view both the webserver (NodeJS) and Metabase error messages from the shell, this then resulted in 2 seperate scripts being created and 2 aliases (start-webserver, start-metabase), I also had to fix an issue with Metabase running on port 3000 as does the nodejs server. I had to implement export calls to set the environment variables for metabase to be on port 17050
Database Updates | 12 | With every change to the datamodel, the servers database had to be updated, quite a lot of changes have been made to the database (as is evident in the GIT history and Discord channel), this resulted in a lot of time spent fixing this
Code / Repository Updates | 8 | As with the Database updates, each time that the code was pushed to dev or something needed to be tested on the server to ensure it worked, I had to pull down the changes and build the files necessary. Further to this any file permission changes had to be handled as well for scripts and any writes, etc.
Bug fixes (Server hangs, Reboots, OS Updates, etc) | 3 | A number of times I had to reboot the server due to the server freezing because of to many instances of Metabase running, something else eating the resources such as errors in code. I also updated the OS and other applications that were running on the server