Transition Iteration Plan 2

# 1. Key milestones

|  |  |
| --- | --- |
| **Milestone** | **Date** |
| Iteration start | 28/09/2018 |
| Team Meeting | 1/10/2018 |
| Iteration Meeting with Jim | 3/10/2018 |
| Team Meeting 2 | 8/10/2018 |
| Iteration stop | 5/10/2018 |

# 2. High-level objectives

1. Complete fixing identified issues discovered during Iteration Plan 1.
2. Update all documentation to reflect current project.

# Evaluation criteria

1. All issues found are resolved
2. Documentation is completed

# 4. Work Item assignments

The following Work Items will be addressed in this iteration:

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Work Item ID** | **Name or key words of description** | **Outcome** | **State** | **Assigned to (name)** | **Estimated Hours** | **Hours worked** | **Estimate of hours remaining** |
| 4.1, 4.2, 4.3, 4.5 | Issue identified with Manage Medication Type/Patient Type/Worker | Resolve an issue affecting the ability to add a record using certain pages. | Irreproducible- Tentatively Complete – See issue 1 | Ryan  Lenny  Beau  Jette | 10 | 0 | 0 |
| 4.4 | Download .csv file | Ensure that a file can be downloaded | Incomplete – see issue 2 | Jette | 10 | 2 | 0 |
| 4.6 | Physician fields validation | When Physician was not notified, physician fields still required data to be entered even though they were disabled | [Complete](https://bitbucket.org/itc303teampharmacon/pharmacy_app/src/dev/code/client/src/components/Error.vue) | Jette Ryan | 5 | 4 | 0 |
| 5.1 | Issue with server running out of memory in Dev / Test Environment. | Separation of Database Server and Front-end webserver | Incomplete | Lenny  Beau | 14 | 0 | 14 |
| 5.2 | Hidden fields | IIMS Completed, Worker Notified and Physician Notified to show correctly when fields have not been hidden. Physician fields not to show at all when either hidden or not notified | [Complete](https://bitbucket.org/itc303teampharmacon/pharmacy_app/commits/2bf487b869bc79048bbb3a8fcb15b9a9eb472847?at=FixHideFieldIssue#chg-code/client/src/components/Error.vue) | Jette Ryan | 5 | 4 | 0 |
| 5.3 | Demonstration Video | Create a demonstration video for Jim by the 10th. Will need to submit a similar, more polished video for final submission. | Incomplete | Lenny | 5 | 0 | 5 |
| 5.4 | Beta tester sign-off | Have the beta-testers re-do the tests to ensure issues are resolved. | Incomplete | Ryan Lenny Beau Jette | 10 | 0 | 10 |

# 5. Issues

|  |  |  |
| --- | --- | --- |
| **Issue** | **Status** | **Notes** |
| Issue 1 – unreproducible error | Resolved | Due to incorrectly interpreting multiple similar beta test reports, this issue was given multiple work items in the initial iteration plan, which have been properly condensed. While a team member was able to witness the error, we have been unable to reproduce the issue despite knowing the exact steps that caused it, and we believe it was a transient issue caused by server resource management problems that we are resolving with work item 5.1 |
| Issue 2 – Download .csv file | Resolved | This feature relies on all tables having data entered. As we are allowing fields to be hidden, some tables will not have any data entered for a specific error. This causes the report not to run. As this feature was not one that we were planning on providing, it has been deleted. |

# 6. Assessment

[[Use this section for capturing and communicating results and actions from assessments, which are typically done at the end of each iteration. . . If you don’t do this, the team may not be able to improve the way they develop software.]

|  |  |
| --- | --- |
| Assessment target | Successful submission of PRM and PMAS |
| Assessment date | 15 October 2018 |
| Participants | Ryan, Beau, Lenny, & Jette |
| Project status | **Green** |

## Assessment against objectives

## Work Items: Planned compared to actually completed

## Assessment against Evaluation Criteria Test results

## Other concerns and deviations